## Slide 1: CONSTRAINT-BASED SCHEDULING and PLANNING
Speaker: Olufikayo Adetunji
CSCE 921
Authors: Philippe Baptiste, Philippe Laborie, Claude Le Pape, Wim Nuijten
CP Handbook, Chapter 22

## Slide 2: Overview
Introduction
  Preliminaries
Constraint Programming Model for Scheduling
  Activities
  Resource Constraints
  Temporal Constraints
  Extensions
  Objective Function
Examples
  Timetabling
  Machine scheduling with disjunctive scheduling
  Machine scheduling with cumulative scheduling
Constraint Propagation for Resource Constraints
  Unary Resource
  Cumulative Resource
Conjunctive Reasoning between Temporal and Resource Constraint
Heuristic Search
Conclusion

## Slide 3: Overview
Introduction
  Preliminaries
Constraint Programming Model for Scheduling
  Activities
  Resource Constraints
  Temporal Constraints
  Extensions
  Objective Function
Examples
  Timetabling
  Machine scheduling with disjunctive scheduling
  Machine scheduling with cumulative scheduling
Constraint Propagation for Resource Constraints
  Unary Resource
  Cumulative Resource
Conjunctive Reasoning between Temporal and Resource Constraint
Heuristic Search
Conclusion

## Slide 4: Preliminaries
The scheduling task is
  to allocate known activities
  to available resources
  over time
  respecting capacity, precedence (and other) constraints
The planning task is
  to construct a sequence of actions
  that will transfer the initial state of the world
  into a state where the desired goal is satisfied
   Tasks are not known in advance
Constraint-Based Scheduling & Constraint-Based Planning
  Solving these problems using Constraint Programming (CP)

## Slide 5: Overview
Introduction
  Preliminaries
Constraint Programming Model for Scheduling
  Activities
  Resource Constraints
  Temporal Constraints
  Extensions
  Objective Function
Examples
  Timetabling
  Machine scheduling with disjunctive scheduling
  Machine scheduling with cumulative scheduling
Constraint Propagation for Resource Constraints
  Unary Resource
  Cumulative Resource
Conjunctive Reasoning between Temporal and Resource Constraint
Heuristic Search
Conclusion

## Slide 6: CP Model for Scheduling
Notations
  Set of Activities: {A1, … , An}
  Set of Resources: {R1, … , Rm}
Scheduling Problem
  A set of activities has to be processed
  By a limited number of resources
  In a limited amount of time

## Slide 7: Example: Bicycle Assembly
3 workers who can perform tasks
10 tasks with its own duration
Precedence constraints (Ti ‹‹ Tj)
  Ti must be processed before Tj
No preemption
  activity cannot be interrupted
  during processing
3
8
2
2
2
8
T10
T8
T6
T4
T9
T5
T3
T2
T7
T1
7
7
18
T1
T2
T7
T4
T10
T8
T6
T5
T3
T9
T4
T10
T8
T6
T5
T3
T9
schedule
optimal schedule
T1
T2
T7

## Slide 8: Activity A
Activity A is an entity needing some resources & time
Variables: start(A), end(A), proc(A)
  start(A): start time of the activity
  end(A): completion time of the activity
  proc(A): processing time (duration) of the activity
Domains: [r,d], time interval A which has to execute

## Slide 9: CSP variables & Domains
start(A): start time of the activity
  activity A cannot start before its release date
  lst(A) = max(start(A)), latest start time
  est(A) = min(start(A)), earliest start time
end(A): completion time of the activity
  activity Amust finish before the deadline
  eet(A) = min(end(A), earliest end time
  lct(A) = max(end(A), latest completion time
proc(A): processing time (duration) of the activity

## Slide 10: Terminology
Preemptive & non-preemptive activities
Disjunctive & cumulative scheduling
Temporal constraints
  Precedence constraints (before, after)
  Disjunctive constraints (not at the same time)
Resources
  Alternative resources
  Reservoirs
  Breakable activities & calendars
  State resources

## Slide 11: Activities: Types
  Non-preemptive activity cannot be interrupted: end(A) – start(A) = proc(A)
  Preemptive activity can be interrupted: end(A) – start(A) ≥ proc(A)
  proc(A) = proc(A[1]) + proc(A[2]) + proc(A[3]) + proc(A[4])
0 1 2 3 4 5 6 7 8 9 10
A
start(A)
end(A)
p(A)
time
0 1 2 3 4 5 6 7 8 9 10 11 12
start(A)
end(A)
time
A[1]
A[2]
A[3]
A[4]

## Slide 12: Resource Constraints
Resources: disjunctive scheduling and cumulative scheduling
Disjunctive scheduling:
  All resources have a unary capacity. i.e., cap(A) = 1
  Resources are called machines
  At most one activity can be executed at a time
Cumulative scheduling:
  Each activity uses some capacity of the resource cap(A)
  Resources can execute several activities in parallel if the resource capacity is not exceeded
  3
  2
  1
0 1 2 3 4 5 6 7 8 9 10 11 12 13 14
A
B
C
D
E
A
C
B
D
0 1 2 3 4 5 6 7 8

## Slide 13: Resource Constraints: disjunctive vs cumulative
Disjunctive scheduling
  All resources have a unary capacity, cap(A) = 1
  Resources are called machines
  At most one activity can be executed at a time
Cumulative scheduling
  Each activity uses some capacity of the resource cap(A)
  Resources can handle several activities at the same time up to resource capacity
  3
  2
  1
0 1 2 3 4 5 6 7 8 9 10 11 12 13 14
A
B
C
D
E
A
C
B
D
0 1 2 3 4 5 6 7 8

## Slide 14: Temporal Constraints
Temporal relations between activities expressed by linear constraints between start and end variables of activities
Precedence constraint between activities A, B (sequencing A‹‹B of activities A,B)
  end(A) ≤ start(B)
Disjunctive constraint: activities A and B cannot overlap
  A‹‹B or B‹‹A
  end(A) ≤ start(B) or end(B) ≤ start(A)
0 1 2 3 4 5 6 7 8 9 10
A
B
time
Notes: For precedence constraint: Activity B is to be started after Activity A has ended
For Disjunctive: This is the constraint involved in the Disjunctive scheduling of resources. Where any 2 non-preemptive activities are related by the disjunctive constraint.

## Slide 15: Extensions: Alternative Resources
Activity A can be scheduled on any one resource from a set S of resources
  S is the set of alternative resources for A
  S is defined by domain variable altern(A)
  Example: Any of the persons can process a set of tasks.
  Resources are unrelated
  Different alternatives can have different costs
Disjunctive scheduling ≡ Alternative unary resources
  Activity can be processed on any of the unary resources
Cumulative scheduling ≡ One cumulative resource with resource capacity corresponding to the number of alternative unary resources

## Slide 16: Extensions: Reservoirs
Reservoir resource can be consumed and/or produced by activities
  Activity consumes some quantity of the resource cap(A)<0
  Activity produces some quantity of the resource cap(A)>0
Cumulative resource is a special case of reservoir
-1
+1
-1
Notes: Cumulative resource is a special case of reservoir that is consumed at the beginning of the activity and produced in the same quantity at the end of the activity when the activity releases the resource

## Slide 17: Extensions: Other types of resources
Breakable activities & calendars
  Resources are governed by a calendar
  Calendar consists of breaks and productivity profile under which activities scheduled on the resource are executed
State resources
  Resource of infinite capacity, with varying state over time

## Slide 18: Optimization: Objective Functions
Optimization problems optimize an objective function
An objective function uses a variable criterion (equals the value of objective function
Makespan (criterion): completion time of the last activity
Modeling the makespan
  Introduce L, proc(L) = 0
  Add precedence constraint for each T with no successor
B
D
C
F
E
A
L
Notes: The commonly used criterion is Makespan. It is commonly modeled as some extra activity L, which gets a precedence constraint from other activities with no successor to it

## Slide 19: Overview
Introduction
  Preliminaries
Constraint Programming Model for Scheduling
  Activities
  Resource Constraints
  Temporal Constraints
  Extensions
  Objective Function
Examples
  Timetabling
  Machine scheduling with disjunctive scheduling
  Machine scheduling with cumulative scheduling
Constraint Propagation for Resource Constraints
  Unary Resource
  Cumulative Resource
Conjunctive Reasoning between Temporal and Resource Constraint
Heuristic Search
Conclusion

## Slide 20: Example: Timetabling Problem
Create a schedule of N periods for classes with
  Given durations
  Given lecturers
  Given number of enrolled students
  Prohibited time periods
M classrooms with specified seat capacities
Where there are sets of classes creating a curriculum
  No class time overlap within the classes of a curriculum

## Slide 21: Timetabling: Variable and Domains
Class = Activity with given duration
Start time variable for each class start(A)
  start(A) = {0, 1, … , N-1}
  start(A) ≠ prohibited(A)
Classrooms = resources
Classrooms are ordered by seat capacity: 0 to M-1
Classroom variable for each class resource(A)
  resource(A) = {K, . . . , M-1} such that K is the smallest classroom where the class fits by the number of students
  4 classrooms with sizes 25, 30, 40, 75 corresponding to 0,1,2,3 class A wants a room with capacity 25: resource(A)={0,1,2,3} class B wants a room with capacity 35: resource(B)={2,3} class C wants a room with capacity 70: resource(C)=3

## Slide 22: Timetabling: Resource Constraints
Teacher represents a unary/disjunctive resource
  a lecturer can teach only one class at a time (no overlap)
  all classes of each lecturer are constrained by unary resource constraint
  classes are represented with their start(A) and proc(A) variables
Curriculum represents a unary resource
  classes of one curriculum cannot overlap
  classes of one curriculum define one unary resource constraint
  classes are represented with their start(A) and proc(A) variables

## Slide 23: Timetabling: Time & classrooms
Constraint:
At most one course must be taught at any classroom at each time slot
All classrooms together represents one unary resource
all classes request this resource
each class is encoded by activity with the starting time start-resource(A) = start(A) + resource(A) * N and duration proc(A)
0 1 2 3
01234567
rooms
periods
Room 0
Room 3
Room 2
Room 1

## Slide 24: Machine scheduling with disjunctive scheduling: Problem & example
Given
A set of tasks with est, lct, proc
Precedence constraints from graph
One machine of a unity capacity
Question: Create a schedule while minimizing the makespan
Task T | est(T) | lct(T) | proc(T)
A | 0 | 10 | 2
B | 0 | 15 | 3
C | 5 | 25 | 4
D | 0 | 20 | 1
E | 10 | 25 | 5
F | 0 | 5 | 3
B
D
C
F
E
A

## Slide 25: Machine scheduling with disjunctive scheduling: Variables
Start time variables start(T) for each task T
Start(T) = {est(T), . . . , lct(T)-proc(T)}
Example
Domains of tasks
A={0..8}, B={0..2}, C={5..21},
D={0..19}, E={10..20}, F={0..2}
Task T | est(T) | lct(T) | proc(T)
A | 0 | 10 | 2
B | 0 | 15 | 3
C | 5 | 25 | 4
D | 0 | 20 | 1
E | 10 | 25 | 5
F | 0 | 5 | 3

## Slide 26: Machine scheduling with disjunctive scheduling: Constraints
Precedence constraints for each tasks T1‹‹T2
start(T1) + proc(T1) ≤ start(T2)
Example: A+2 ≤ B, B+3 ≤ C, F+3 ≤ E, E+5 ≤ C, D+1 ≤ C,
Unary resource for all tasks T given by
start time variables start(T)
duration p(T)
Example: serialized([A,B,C,D,E,F],[2,3,4,1,5,3])
B
D
C
F
E
A
Task T | est(T) | lct(T) | proc(T)
A | 0 | 10 | 2
B | 0 | 15 | 3
C | 5 | 25 | 4
D | 0 | 20 | 1
E | 10 | 25 | 5
F | 0 | 5 | 3

## Slide 27: Machine scheduling with disjunctive scheduling: Optimization
New task L with proc(L)=0 added
Precedence constraints
  between L and tasks with no successor added
Example: C+4 ≤ L
B
D
C
F
E
A
L
Minimize(makespan) = Minimize(startL)

## Slide 28: Machine scheduling with disjunctive scheduling: Solution
Task T | est(T) | lct(T) | proc(T)
A | 0 | 10 | 2
B | 0 | 15 | 3
C | 5 | 25 | 4
D | 0 | 20 | 1
E | 10 | 25 | 5
F | 0 | 5 | 3
B
D
C
F
E
A
0 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20
F
A
D
E
B
C
time

## Slide 29: Machine scheduling with cumulative scheduling: Problem and Example
Problem: Create a schedule for several tasks with:
earliest start time (est) and latest completion time (lct)
processing time proc
capacity of resource cap
precedence constraints from graph
on machine of capacity 3 such that the makespan is minimized.
B
D
C
F
E
A
Task T | est(T) | lct(T) | proc(T) | cap(T)
A | 0 | 10 | 2 | 1
B | 0 | 15 | 3 | 2
C | 5 | 25 | 4 | 2
D | 0 | 20 | 1 | 3
E | 10 | 25 | 5 | 2
F | 0 | 5 | 3 | 2

## Slide 30: Machine scheduling with cumulative scheduling: Problem & Example
B
D
C
F
E
A
Task T | est(T) | lct(T) | proc(T) | cap(T)
A | 0 | 10 | 2 | 1
B | 0 | 15 | 3 | 2
C | 5 | 25 | 4 | 2
D | 0 | 20 | 1 | 3
E | 10 | 25 | 5 | 2
F | 0 | 5 | 3 | 2
Given
A set of tasks with est, lct, proc
Capacity of resource cap = 3
Precedence constraints from graph
Question: Create a schedule while minimizing the makespan

## Slide 31: Machine scheduling with cumulative scheduling: Modeling
Same model as for scheduling with unary resource with
  unary resource replaced by cumulative resource
Cumulative resource for all tasks T given by
  start time variables start(T)
  duration proc(T)
  requested capacity of the resource
Example: cumulative([A,B,C,D,E,F],[2,3,4,1,5,3],[1,2,2,3,2,2],3)
Task T | est(T) | lct(T) | proc(T) | cap(T)
A | 0 | 10 | 2 | 1
B | 0 | 15 | 3 | 2
C | 5 | 25 | 4 | 2
D | 0 | 20 | 1 | 3
E | 10 | 25 | 5 | 2
F | 0 | 5 | 3 | 2

## Slide 32: Machine scheduling with cumulative scheduling: Solution
0 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20
F
A
D
E
B
C
time
B
D
C
F
E
A
0 1 2 3
resource capacity
Task T | est(T) | lct(T) | proc(T) | cap(T)
A | 0 | 10 | 2 | 1
B | 0 | 15 | 3 | 2
C | 5 | 25 | 4 | 2
D | 0 | 20 | 1 | 3
E | 10 | 25 | 5 | 2
F | 0 | 5 | 3 | 2

## Slide 33: Overview
Introduction
  Preliminaries
Constraint Programming Model for Scheduling
  Activities
  Resource Constraints
  Temporal Constraints
  Extensions
  Objective Function
Examples
  Timetabling
  Machine scheduling with disjunctive scheduling
  Machine scheduling with cumulative scheduling
Constraint Propagation for Resource Constraints
  Unary Resource
  Cumulative Resource
Conjunctive Reasoning between Temporal and Resource Constraint
Heuristic Search
Conclusion

## Slide 34: Constraint Propagation for Resource Constraints: Unary resources - Notations
est(A) earliest start time of activity A
ect(A) earliest completion time of activity A
lst(A) latest start time of activity A
lct(A) latest completion time of activity A
Ω is the set of activities
pΩ = ∑A∈Ω p(A)
rΩ = min{est (A) | A ∈ Ω}
dΩ = max{lct (A) | A ∈ Ω}

## Slide 35: Unary resources: disjunctive constraint propagation
2 activities A and B, requiring the same unary resource cannot overlap in time.
Solution:
A‹‹B ˅ B‹‹A
Ensure no overlap with formula:
[end(A) ≤ start(B)] ˅ [end(B) ≤ start(A)]
Whenever:
  d(A) > r(B) ⇒ B<<A
  d(B) > r(A) ⇒ A<<B
If none holds then there is a contradiction

## Slide 36: Unary resources: Edge-finding
What can we notice?
How do we fix this?
B(6)
A(9)
B(6)
A(9)
3
20
20
7
3
14
20
7

## Slide 37: Unary resources: Edge-finding
Edge-finding involves deducing that some activity from a given set Ω must, can, or cannot execute first (last) in Ω
  The basic rules are as follows (for all Ω, and for all A not in Ω):
Edge-finding rules
  pΩ ∪ {A} > dΩ ∪ {A} − rΩ ⇒ A<<Ω
  A << Ω ⇒ end(A) ≤ min{dΩ′ − pΩ′ | Ω′ ⊆ Ω}
Edge-finding (symmetrical rules)
  pΩ ∪ {A} > d(Ω − rΩ ∪ {A} ⇒Ω<<A
  Ω << A ⇒ start(A) ≤ max{rΩ′ + pΩ′ | Ω′ ⊆ Ω}
Notes: If the sum of the minimal processing time of set union A is greater than max lct of set union A minus min est set then A preceeds set
If A preceeds set, then the end of A is less than or equals the min of (max lct of set minus sum of minimal proc time of set).
Set’ is what is left after a rule has been applied

## Slide 38: Unary resources: Edge-finding
Applying a rule to the example
  pΩ ∪ {A} > dΩ ∪ {A} − rΩ ⇒ A<<Ω
  A << Ω ⇒ end(A) ≤ min{dΩ′ − pΩ′ | Ω′ ⊆ Ω}
B(6)
A(9)
B(6)
A(9)
3
20
7
3
12
20
7
20
17>(20-7)
12≤(20-6)

## Slide 39: Unary resources: Not-first and Not-last rules
What of this?
How do we fix it?
A(8)
B(5)
3
20
20
7
C(5)
20
9
A(8)
B(5)
3
20
20
7
C(5)
20
9

## Slide 40: Unary resources: Not-first and Not-last rules
Negative counterpart to edge-finding.
Deduces that an activity A cannot be first (or last) to execute in Ω ∪ {A}
“not first” rules (for all Ω, and for all A not in Ω):
  p(Ω ∪ {A}) > dΩ − rA ⇒ start(A) ≥ min{ect(B )|B ∈ Ω}
“not last” rules (for all Ω, and for all A not in Ω):
  p(Ω ∪ {A}) > dA − rΩ ⇒ end(A) ≤ max{lst(B )|B ∈ Ω}

## Slide 41: Unary resources: Not-first and Not-last rules
p(Ω ∪ {A}) > dA − rΩ ⇒ end(A) ≤ max{lst(B )|B ∈ Ω}
18 > (20-7) ⇒ 11 ≤ 15
A(8)
B(5)
3
12
20
7
C(5)
20
9
A(8)
B(5)
3
20
20
7
C(5)
20
9

## Slide 42: Constraint Propagation for Resource Constraints: Cumulative resources
Each activity uses some capacity of the resource cap(A)
Activities can be processed in parallel, if a resource capacity is not exceeded

## Slide 43: Cumulative resources: Timetable Constraint (Example)
Initial case
Restrictions caused by capacity
Solution
0
{0,1}
0
r(A)
d(A)
lst(a)
ect(A)
X{A,t}
0
{0,1}
0
r(A)
d(A)
lst(a)
ect(A)
X{A,t}
{0,1}
0
0
{0,1}
0
r(A)
d(A)
lst(a)
ect(A)
X{A,t}
{0,1}
1

## Slide 44: Cumulative resources: Timetable Constraint
The timetable is used to maintain information about resource utilization and resource availability over time.
Time must be discrete
We do not want the capacity to be exceeded
∀t ∑ cap(Ai) ≤ MaxCapacity
Timetable for activity A is a set of Boolean domain variables X (A, t )
∀t ∑ cap(Ai) ≤ MaxCapacity
where, start(Ai) ≤ t ≤ end(Ai) ⇔ X (Ai, t)
start(Ai)≤t≤end (Ai)
Ai
Notes: The propagation mainly consists of maintaining for any time t arc-B-consistency

## Slide 45: Cumulative resources: Disjunctive constraint
A and B are activities:
min(cap(A)) + min(cap(B)) > MaxCapacity
A and B cannot overlap: A‹‹B ˅ B‹‹A (disjunctive constraint)
[cap(A) + cap(B) ≤ MaxCapacity] ˅ [end(A) ≤ start(B)] ˅ [end(B) ≤ start(A)]
Notes: The formula is used to maintain arc-B-consistency

## Slide 46: Cumulative resources: Energy Reasoning
Compares the amount of energy provided by a resource
  over some interval [t1, t2)
  to the amount of energy required by activities that have to be processed over this interval
  i.e., the minimal contribution WSh(A, t1, t2) of each activity to a given interval.

## Slide 47: Cumulative resources: Energy Reasoning
Given A and [t1, t2):
“Left-Shift/Right-Shift” WSh(A, t1, t2) = min(cap(A))*min(t2-t1, p+(t1), p-(t2))
  t2-t1: the length of the interval
  p+(t1) = max(0, p – max(0, t1 - r)): No of time units during which A executes after time t1 if A is left-shifted, i.e., scheduled as soon as possible
  p-(t1) = max(0, p – max(0, d - t1)): No of time units during which A executes after time t1 if A is left-shifted, i.e., scheduled as soon as possible

## Slide 48: Cumulative resources: Energy Reasoning
Given A and [t1, t2):
“Left-Shift/Right-Shift” WSh(A, t1, t2) = min(cap(A))*min(t2-t1, p+(t1), p-(t2))
  WSh(A, 2, 7) = 2 min(5,5,4) = 8
 | r | d | p | min(cap)
A | 0 | 10 | 7 | 2
0
1
2
3
5
4
6
7
8
9
10

## Slide 49: Overview
Introduction
  Preliminaries
Constraint Programming Model for Scheduling
  Activities
  Resource Constraints
  Temporal Constraints
  Extensions
  Objective Function
Examples
  Timetabling
  Machine scheduling with disjunctive scheduling
  Machine scheduling with cumulative scheduling
Constraint Propagation for Resource Constraints
  Unary Resource
  Cumulative Resource
Conjunctive Reasoning between Temporal and Resource Constraint
Heuristic Search
Conclusion

## Slide 50: Conjunctive Reasoning between Temporal and Resources Constraint
Propagation techniques that reason on
  the combination of time bounds of activities on multiple unary resources and
  the temporal constraints linking these activities
  Precedence Graph
Propagation techniques that reason on
  the combination of activity time bounds and temporal constraints
  on one cumulative resource.
  Energy precedence constraint

## Slide 51: Precedence Graph
Maintenance of a temporal network representing the relations between time points of all activities (start and end times) using the point algebra
Relations between time points are denoted by:
{≠, =, ≾, ≿, ≺, ≻, ?, ∅}
For example:
end(B) ≤ start(A) implies there is a temporal relation
in the precedence graph where e(B) ≾ s(A)
Notes: Qualitative relations between time points.

## Slide 52: Energy Precedence Constraint
Energy precedence propagation for an activity A on a cumulative resource R
  Ensures that for each subset Φ of predecessor activities of A
  The resource provides enough energy to execute all activities
  In Φ between rΦ and s.
∀Φ⊆{B | eB≾sA} start(A) ≥ rΦ + ┌EΦ/cap(Rk)┐

## Slide 53: Overview
Introduction
  Preliminaries
Constraint Programming Model for Scheduling
  Activities
  Resource Constraints
  Temporal Constraints
  Extensions
  Objective Function
Examples
  Timetabling
  Machine scheduling with disjunctive scheduling
  Machine scheduling with cumulative scheduling
Constraint Propagation for Resource Constraints
  Unary Resource
  Cumulative Resource
Conjunctive Reasoning between Temporal and Resource Constraint
Heuristic Search
Conclusion

## Slide 54: Heuristic Search
Same principles around search in CP
Constraint propagation is not enough
  Use heuristic search to generate solutions
When solution is found, heuristic search will either stop (if solution is ok) or continue (require a lower cost)
If continuing, add a constraint that states the need for a solution with a lower cost
Multiple criteria ⇒ set of constraints
  Slow-down some criteria if it improves others
Basic heuristic: Focus on the more constrained variables first

## Slide 55: Heuristic Search: Branching Strategy
Choosing the right branching strategy depends on the optimization criteria
Regular: An optimization criteria to minimize (e.g. makespan)
  If it increases with the end times of the activities
  Solution S1 is strictly better than S2 if some activity A finishes earlier in S1
  Solve resource constraints by ordering activities
  On any given branch, the value of criterion obtained by replacing each end time variable by its lower bound is a lower bound for the optimization function.
  Possibility of the dominance properties
Notes: Other regular criteria include: avg completion time, maximal or weighted tardiness, weighted number of late activities

## Slide 56: Heuristic Search: Branching Strategy
Choosing the right branching strategy depends on the optimization criteria
Sequence-dependent: if it depends only on the relative order in which activities are executed
  Solve resource constraints by ordering activities
  The est and ect that result from constraint propagation can be used as a solution
  Dominance properties cannot be applied
  After solving, a linear program can be used to determine the optimal solution for the chosen sequences
Notes: Example: sum of setup times and the sum of setup cost

## Slide 57: Heuristic Search: Local search
Very large search spaces
Look for “good” solutions
Local-search is used by
  Mixing constraint-based search with Local search (taken as alternative to explore search space)
  Implementing local search with constraint
Local moves considered are
  “Repair” moves swap two activities scheduled on same machine to shrink or reduce the number of critical paths
  “Shuffle” moves keep part of the solution and search through the rest of the solution space to complete it
Notes: Critical path: a sequence of activities where i) for each activity A that appears before activity B in the sequence A indeed precedes B in the schedule and ii) the sum of the processing times of the activities in the sequence equals the makespan of the schedule.

## Slide 58: Heuristic Search: Mixed Integer Programming
Hybrid combination of CP and MIP.
More efficient in most cases than the individual ones
The optimal continuous solution of the linear sub-problem is guaranteed to be integral
  Solution either satisfies all resource constraints and is optimal; or
  Violates some resource constraint which can be used to branch on the order of two conflicting activities
CP is used to limit and select the explored branches
Notes: Critical path: a sequence of activities where i) for each activity A that appears before activity B in the sequence A indeed precedes B in the schedule and ii) the sum of the processing times of the activities in the sequence equals the makespan of the schedule.

## Slide 59: Questions and Discussion
Thank You